## Sheet1
Task:-	Duration:-	Start:-	Finish
GATHERING REQUIREMENTS AND PLANNING PHASE	15 days	Wed 28-11-2018	Wed 12-12-2018
Scope of Project	2 days	Wed 28-11-2018	Thu 29-11-2018
Functional and Non Functional Requirements	4 days	Fri 30-11-2018	Mon 3-12-2018
Use Case Diagram	2 days	Tue 4-12-2018	Wed 5-12-2018
Usage Scenarios	3 days	Thu 6-12-2018	Sat 8-12-2018
Adopted Methodologies	2 days	Sun 9-12-2018	Mon 10-12-2018
Work Plan	2 days	Tue 11-12-2018	Wed 12-12-2018
Design Phase	40 days	Thu 13-12-2018	Mon 21-1-2019
Introduction to Design Document	5 days	Thu 13-12-2018	Mon 17-12-2018
Entity Relation Diagram	5 days	Tue 18-12-2019	Sat 22-12-2018
Sequence Diagram	4 days	San 23-12-2018	Wed 26-12-2018
Architecture Design Diagram	5 days	Thu 27-12-2018	Mon 31-12-2018
Class Diagram	5 days	Tue 01-01-2019	Sat 05-01-2019
Database Diagram	6 days	Sun 06-01-2019	Fri 11-01-2019
Interface Diagram	10 days	Sat 12-01-2019	Mon 21-1-2019
DEVELOPMENT AND FINAL REPORT PHASE	106 days	Mon 22-1-2019	Tue 7-05-2019
Development	86 days	Tue 22-01-2019	Wed 17-04-2019
Final Report	15 days	Thu 18-04-2019	Thu 02-05-2019
Final Presentation	5 days	Fri 3-05-2019	Tue 7-05-2019